## Slide 1: Using Federal Funds through NCDOT
Copy/paste any of the icons below into your presentation. Please change color to white if using them on a dark background.

## Slide 2: Presentation Overview
PART I : Major Requirements of the Federal Highway Administration (“Big Rocks”)
  Applies to all sources of Federal funding (TAP, STBG, CRP, CMAQ, Discretionary Grants (RAISE, Earmarks, etc.)
  Requirements have increased over the past 15 years.
PART II : Planning Your Project Proposal (breaking down the “Big Rocks”)
  How to factor in Federal requirements
  Factors to be aware of that will increase your costs and delay your schedule

## Slide 3: Federal Requirements
“Big Rocks”

## Slide 4: Federal Highway Administration (FHWA)
Administration of Federal Funds governed by the Stewardship and Oversight Agreement
  Outlines responsibilities of NCDOT to provide oversight of funding
  Lists those responsibilities that cannot be delegated to the State
  Includes detailed requirements for oversight of Local Projects
Title 23 of the Code of Federal Regulations governs Highways

## Slide 5: Funding Authorization
FHWA authorizes funding by phases:
  Preliminary Engineering (design and environmental documentation)
  Right of Way / Utility Relocation
  Construction
  NCDOT cannot request authorization of funds until certain deliverables are met (23 CFR 630) Project Authorization and Agreements
  Any costs incurred prior to funding authorization are not eligible for reimbursement
  (23 CFR 1.9(a)) Limit on Federal Participation
  T
  (23 CFR 1.9(a))

## Slide 6: Consultant Procurement
FHWA establishes a process for procurement/administration of consultant contracts that utilize Federal funds:
  Selection must be based on qualifications
  Consultant rates must be audited by NCDOT
  Contract language must include Federal provisions
(23 CFR 172) – Procurement, Management and Administration of Engineering and Design Related Services

## Slide 7: National Environmental Policy Act (NEPA)
All Projects must meet requirements of NEPA
  Qualified personnel required to complete environmental surveys/assessments
  NCDOT must concur with the environmental documents
  Documents must be current (less than 1 year old) to authorize funds
(23 CFR 771) – Environmental Impact and Related Procedures

## Slide 8: Right of Way
All Right of Way Acquisition must meet the “Uniform Act”
  Property owners are entitled to an appraisal
  Fair Market Value and Just Compensation is reviewed by NCDOT
  ROW requirements apply whether Federal funds are used for ROW or not
(23 CFR 710) – Right of Way and Real Estate
(49 CFR 24) – Uniform Relocation Assistance and Real Property Acquisition for Federal and Federally-Assisted Programs

## Slide 9: Construction Contracts
Contract Proposals must include Federal-aid contract provisions:
  Davis-Bacon and minimum wage requirements
  Disadvantaged Business Enterprises (DBE) goals to utilize minority businesses
  Americans with Disabilities (ADA) Act
  Buy America – expanded to include construction materials (not just iron and steel)
  Title VI, etc.
  (23 CFR 633) – Required Contract Provisions

## Slide 10: Construction Contract Administration
Advertising, Letting and Awarding Contracts must comply with Federal requirements
  Advertisement for 3 weeks
  No negotiation with contractor is allowed
  NCDOT must concur in the award of contract to the responsible low bidder
  NCDOT’s Construction Manual and Standard Specifications will be utilized
  (23 CFR 635) – Construction and Maintenance

## Slide 11: Multiple Governmental Partners
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.
Keep in mind that you will be dealing with three layers of bureaucracy – local, state, and Federal. The good news is that our office, the Division and FHWA all work together to ensure that all projects meet requirements, and we can reimburse your costs.

## Slide 12: Planning Your Project Proposal
Breaking down the “big rocks”

## Slide 13: PROJECT DELIVERY
Major Emphasis with NCDOT
Locally Administered Projects (LAPs) are in the STIP – must have a schedule!
When milestones are missed, EVERYONE gets questions
Be REALISTIC when setting schedules
Expect the Unexpected
Project completion occurs after completion of construction – must close out Projects to complete
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 14: MAJOR SHOW STOPPERS
FEASIBILITY
POORLY DEFINED SCOPE
CONSTRUCTABILITY
AVAILABLE RIGHT OF WAY
EXTENT OF UTILITY CONFLICTS
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 15: MAJOR SHOW STOPPERS
FUNDING
Unrealistic Estimates
Scope Creep (or Scope Reduction)
Inaccurate quantities (or no quantities)
No estimate for Right of Way
No estimate for Utility Relocation
Environmental Issues
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 16: UNREALISTIC ESTIMATES
Do not use bid prices from a previous project
NCDOT publishes average bid prices
Re-advertising issues/problems
Adjusting engineer’s estimate
Negotiating with bidders not permitted
Cost Escalation
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 17: RIGHT OF WAY ISSUES
All ROW incorporated into Project must be certified
Must follow the “Uniform Act”
Condemnation
Multiple Property Owners
Title Issues
***This phase always takes longer than you think***
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 18: UTILITY ISSUES
Power company will not begin engineering until plans are complete, at least up to Hydro
What about utilities underground (communication, gas, water/sewer)
Most underground utilities are by encroachment
Permanent Utility Easements (PUEs)
Utility /RR Certification
Utilities can get pricey
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 19: OTHER ADMINISTRATIVE COSTS
Funds for each phase of work must be authorized prior to any work being performed
PE is around 10-15% of your construction cost
ROW costs can be harder to predict
Contract Administration/Construction Engineering and Inspection (CEI) shouldn’t exceed 15% of construction contract, but exceptions can be made
Review and Oversight Agreements for NCDOT’s review of plans prior to Federal Fund availability
NCDOT COSTS – We will charge to your project, be prepared for NCDOT’s review costs.
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.

## Slide 20: PLANNING RESOURCES FOR PROJECT PROPOSALS
Federal-aid Essentials for Local Public Agencies
https://www.fhwa.dot.gov/federal-aidessentials/
Bicycle and Pedestrian Scoping Guidance
https://connect.ncdot.gov/projects/BikePed/Pages/default.aspx

## Slide 21: Project Delivery Resources

## Slide 22
RESOURCES
https://connect.ncdot.gov/municipalities/Funding/Pages/default.aspx

## Slide 23
RESOURCES
https://connect.ncdot.gov/municipalities/Funding/Pages/default.aspx

## Slide 24
LOCAL PROJECT MANAGEMENT TOOL
The Project Management Tool on the EBS Portal will be used to:
Request New Agreements and Supplemental Agreements
Submit Documents for review by the Department
Request Funding Authorizations for each phase of work
Submit Reimbursement Requests for work performed

## Slide 25: QUESTIONS?

## Slide 26
Stephen J. Robinson, PE
sjrobinson@ncdot.gov
336-487-0000 O
Sheila Gibbs
sbgibbs@ncdot.gov
919-707-6625 O
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.
Raymond Hayes, PE
Ext-rjhayes@ncdot.gov
919-628-8999 M
Local Programs Management Office
DIVISION 5
DIVISION 7

## Slide 27
Other slide variations are available. Select Insert above and choose “new slide” to see all the options.